## Sheet1
Assignment - Core Banking - Java With React
Note: | This will Include react and spring
You need to figureout the tables in a database
You are open to add tables and make sure the menaingful fields are ther along with relationships
You are add extra features to project
SPRINT # | User Story | TASK NAME | Status
SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App
2. Install and configure React Router for handling routing in the application
3. Set up a new springboot project and all the required dependencies and test working fine or not
| US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the Core banking system
2. Create the table for registered Customer
3. Create the table for the Account
4. Create the table for Transactions
5. Create the table for interest calculation
6. Identify the relation between the table as per the business requirement.
7. Populate all the above tables with sample data space
8. Create currency conversion table.
| US_03 - As a frontend developer, create a customer registration form that allows to fill out details and register as a new customer and have that information securely processed by the backend system. | 1. Create a react login component to create customer details and provide required validations
2. Write a api end point in springboot to add a new customer details in database
3. Create a react component to update the customer details.
4. Write an api endpoint to work update the specified customer details.
5. Create a react component to list all the customers.
6. Write an endpoint to return list of customer
7. Add feature to search a customer based on id or name in cusomter list page.
8. Write an endpoint to search a customer based on id or name.
| US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. Add an option in existing login component to validate the existing username and password
2. Create an api endpoint in spring boot to accept the user name and password to validate the user.
3. Include the Authentication and Authorization techniques using JWT spring security
4. Perform the session management.
| US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered Customer without account id.
3. Write the backend springboot api endpoint to read account details, geenrate the account id and add it to database.
4. Create a react form to update an existing the account information for a customer.
5. Create an api endpoint to handle the updation in customer information in backend.
6. Create an option on account information page to disable the account or to close the account.
SPRINT - 02 Account Management & User Dashboard | US_06 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components
2. Perform integration testing to validate the interaction between frontend and backend
3. Set up a new springboot project and all the required dependencies and test working fine or not
| US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Create a component to see existing customer's balance with multipe currency option.
2. Write the springboot implementation to fetch balance from table based on selected currency option and send to UI
2. Create form to show all transaction history from current date or specifed date till date with multiple currency option
3.Write the springboot implementation to fetch all transactions for respective user and send to UI
3. Create a form to perform cheque clearance process with required validation
4. Write an endpoint in spring boot to handle the cheque clereance process.
| US_08 - As a developer, create the backend to be equipped with the necessary functionality to support and handle all the APIs related to US_7. This will ensure that an end user can seamlessly interact with the application and access the specific features and data associated with US_7. | 1. Create a component to withdraw the amount with valid required details.
2. write the springboot implementation to update the balance after withdraw of given amount
3. Create a component to deposit the amount with valid required details.
4. Write the springboot implementation to update the balance after deposit of given amount.
5. Create an endpoint to clear the cheque with required validation.
| US_09 - As a developer, create a front end page to perform , interest calculation and funds transfer facility and show the transactoin history. | 1. Create a form to perform the fund transfer from exting active account to another .
2. Write an endpoint in spring boot to transfer the amount trom one acccount to another.
3. Create a react page to calulate the interest on all accounts.
4. Write an api endpoint to calculate the interest based on interest rate and account type.
5. Make sure Swagger and zipkin is added to project.
| US_10 - As a developer, create a repors for admin to have a comprehensivedetails where admin can perform a variety of activities and manage the system effectively. | 1. Create an UI for admin to display his various operations like, active accounts, disabled accounts etc.,
2. Write a api endpoint to display the active and disabled account.
3. Create a report to display interest certificate of specified year.
4. Write an api endpoint to calculate the total availed interest on a particular acccount.
SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc.,
2. Implement the custom exception logic at UI level
3.All input validations logic must be performed at UI level
4. All data validations must be performed at backend
| US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components
2. Perform integration testing to validate the interaction between frontend and backend
3. Set up a new springboot project and all the required dependencies and test working fine or not
| US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page
2. Improve the user interface by adding responsive design, styling, and enhancing the user experience
3. Ensure accessibility and compatibility across different browsers